SC SP - ACTION PLAN 2024-2025

ICAR – KVK, Hans Roever Campus, Perambalur

Submitted to

ICAR - Agricultural Technology Application Research Institute

CRIDA Campus, Santosh Nagar, Hyderabad

FORMAT FOR ACTION PLAN OF

SCSP 2024-2025

Name of the KVK :Hans Roever KVK			District: Perambalur					State: TamilNadu

Table 1 :  Details of  SCSP Operational villages during 2024-25

| S. No. | Name of the operational village (s) | Year of Start | Major occupation of the people | Thrust areas identified based on problems | % SCpopulation with names of major |
| --- | --- | --- | --- | --- | --- |
| 1 | Ladapuram | 2023 | Agriculture and allied fields | Trainings /Extension Activity | 33% |
| 2 | Mettupalayam | 2023 | Agriculture and allied fields | OFT/FLD/Trainings/Extension Activity | 32% |
| 3 | Noothappur | 2023 | Agriculture and allied fields | OFT/FLD/Trainings/Extension Activity | 26% |
| 4 | Keezhapuliyur | 2023 | Agriculture and allied fields | OFT/FLD/Trainings/Extension Activity | 43% |
| 5 | Therani | 2022 | Agriculture and allied fields | Trainings /Extension Activity | 33% |
| 6 | Siruvayalur | 2024 | Agriculture and allied fields | Trainings/Extension Activity | 16% |
| 7 | Pasumbalur | 2023 | Agriculture and allied fields | Trainings/Extension Activity | 36% |
| 8 | Thevaiyur | 2023 | Agriculture and allied fields | Trainings/Extension Activity | 35% |
| 9 | Kurur | 2023 | Agriculture and allied fields | OFT/FLD/Trainings/Extension Activity | 20% |
| 10 | Valikandapuram | 2023 | Agriculture and allied fields | Trainings/Extension Activity | 20% |
| 11 | Melapuliyur | 2023 | Agriculture and allied fields | Trainings/Extension Activity | 31% |
| 12 | Nerkunam | 2023 | Agriculture and allied fields | Trainings/Extension Activity | 10% |
| 13 | Kurumbalur | 2023 | Agriculture and allied fields | Trainings/Extension Activity | 15% |
| 14 | Brahmadesam | 2023 | Agriculture and allied fields | Trainings /Extension Activity | 20% |
| 15 | Anukkur | 2023 | Agriculture and allied fields | Trainings /Extension Activity | 20% |

Table2 :Action Plan for On-farm Testing (Assessment) during 2024-25

| S. No | Year of start | Title of the OFT | Season | No. of farmers | Area (ha) | Technology option 1 | Technology option 2 | Farmers practice | Budget (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2024 | Assessment of Groundnut varieties (CO8 and TCGS 1694) for Perambalur District (Rs. 9350/ trial) | Rabi | 2 | 1 | TO1- Groundnut variety CO8 | TO2- Groundnut variety TCGS 1694 | FP - Groundnut variety TMV 7 | 18700 |
| 2 | 2024 | Assessment of chilli hybrids suitable for Perambalur district (Rs. 5750/ trial) | Kharif | 2 | 1 | Chilli hybrid CO1 | Arka haritha | Private hybrid | 11500 |
| 3 | 2024 | Assessment of IPM modules against sucking pest complex in Cotton (Rs. 4540/ trial) | Kharif | 2 | 1 | TO1- Seed treatment with Beauveria bassiana @ 10 g/kg of seed +Soil application of neem cake @ 250 kg/ha, Yellow sticky trap @ 100 nos./ha, Release of Green lacewing @ 1 lakh eggs/ha at 30 DAS Need based spraying of Azadirachtin1% EC @ 1000 ml/ha Need based spraying of Diafenthiuron 50% WP @ 600 g/ha or Thiamethoxam25% WG @ 100g/ha TNAU CPG, 2020 | TO 2 - Installation of Yellow sticky trap @ 8/acre Maize as border crop Spraying Azadirachtin1% EC Spraying of Lecanicillium lecanii 10gm/l Need based spraying of Flonicamid 50 WG 4g/10litre of water CICR, 2019 | FP - Spraying of Profenofos 50.00% EC, Imidacloprid 17.8 SL/Acephate 75.00% SP | 9080 |
|  |  |  |  | 6 | 3 |  |  | Total | 39280 |

Table3 : Action Plan for Front Line Demonstrations during 2024-25

| S.No | Title of the FLD | Season | Demonstration details | Farmers practice | Area (ha) | No. of farmers | Budget (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Demonstration of Greengram Variety VBN5 for Perambalur district (TNAU, 2022) (Rs. 1790/ demo) | Rabi | Demonstration on greegram variety VBN 5, Seed treatment with Rhizobium and Phosphobacteria @ 10g/kg of seeds, TNAU pulse wonder @ 5 kg ha-1 at peak flowering stage | Cultivation of greegram variety VBN 1 | 4 | 5 | 8950 |
| 2 | Demonstration Blackgram Variety VBN 11 for Perambalur district (TNAU, 2022) (Rs. 1340/ demo) | Rabi | Demonstration on Blackgram variety VBN 11, Seed treatment with Rhizobium and Phosphobacteria @ 10g/kg of seeds, TNAU pulse wonder @ 5 kg ha-1 at peak flowering stage | Cultivation of Blackgram variety VBN 11 | 4 | 3 | 4020 |
| 3 | Cultivation of tuberose variety Arka Prajwal with ICM practices (Rs. 12000/ demo) | Kharif | Cultivation of tuberose variety Arka Prajwal with ICM practices | cultivation of local variety | 2 | 1 | 12000 |
| 4 | Demonstration of IIHR vegetable special micronutrient spray for small onion (Rs. 1000/ demo) | Rabi | Vegetable special micronutrient spray in small onion@5g/ lit at 25th and 35th DAP | no Mn application | 2 | 10 | 10000 |
| 5 | Demonstration on Mung bean Yellow Mosaic Virus (MYMV) resistant LBG 884 Blackgram variety (ANGRAU, 2022) (Rs. 2250/ demo) | Rabi | Demonstration on Mung bean Yellow Mosaic Virus (MYMV) resistant LBG 884 Blackgram variety | Cultivation of susceptible variety | 4 | 3 | 6750 |
| 6 | Demonstration of Namakkal Gold Quail for enhancing egg production (Rs. 2000/ demo) | - | Demo on brooding techniques | - | - | 3 | 6000 |
| 7 | Demonstration of milk replacer for lambs / kids (Rs. 1500/ demo) | - | Demo on milk replacer | - | - | 3 | 4500 |
|  |  |  |  |  | 16 | 28 | 52220 |

Table4 :  Action Plan for Training Programmes during 2024-25

( Small& marginal tribal farmers / farm women)

| S.No | Title of the training programme | Venue (On/Off campus) | Name of the tribal village if off campus | Dates (month) | Duration | No. Trainees (No.) | Budget (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Quail rearing | Off campus | Mettupalayam | September | 1 | 25 | 5000 |
| 2 | Integrated crop Management in Maize | On campus | - | August | 1 | 25 | 5000 |
| 3 | Processing and Value Addition in Millets | On campus | - | September | 1 | 25 | 5000 |
| 4 | ICM in small onion | Off campus | Echampatti | february | 1 | 25 | 5000 |
|  |  |  | Total |  | 5 | 100 | 20000 |

Table5 : Action Plan for Training Programmes during  2024-25 (Rural Youth)

| S.No | Title of the training programme | Venue (On/Off campus) | Name of the tribal village | Dates ( month) | Duration | Trainees (No.) | Budget (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Poultry rearing | On campus | - | August | 1 | 20 | 4000 |
| 2 | Vermicompost production | On campus | - | September | 1 | 20 | 4000 |
| Total |  |  |  |  |  |  | 8000 |

Table 6 :  Action Plan for Training Programmes during 24-25 ( Extension functionaries)

| S.No | Title of the training programme | Venue (On/Off campus) | Name of the tribal village | Dates ( month) | Duration | Trainees (No.) | Budget (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Establishment of Nutrition Garden | On | - | October | 1 | 20 | 4000 |
| Total |  |  |  |  |  |  | 4000 |

Table 7: Action Plan for Skill Training Programmes during 2024-25

| S.No | Title of the training programme | Venue (On/Off campus) | Name of the tribal village | Dates (month) | Duration | Trainees (No.) | Budget (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Dairy farming and management | On campus | - | August | 5 days | 20 | 20000 |
| 2 | Organic input production | On campus | - | December | 5 days | 15 | 15000 |
| 3 | Processing and value addition in fruit, vegetables and medicinal plants | On campus | - | October | 5 Days | 20 | 20000 |
| Total |  |  |  |  |  |  | 55000 |

Table8 :Supply of seed to tribal farmers ( q)2024-25

| S.No. | Crop | Variety | Season | Quantity tobe supplied (q) | Budget (Rs.) |
| --- | --- | --- | --- | --- | --- |
| 1 | Fodder | CoFS29 | Kharif/Rabi | 0.02 | 11000 |
| 2 | Groundnut | Girinar | Rabi | 8 | 104000 |
| Total |  |  |  |  | 115000 |

Table9: Supply of planting material during2024-25

| S.No. | Nature of the material supplied | Crop | No. of seedlings | Budget (Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Vegetables | Tomato, Brinjal, Chillie and Small onion | 20000 | 30000 |
| Total |  |  |  | 30000 |

Table 10: Supply of  livestock / fish fingerlings   during 2024-25

| S.No. | Nature of the material supplied | Units (No. Of livestock/fish fingerlings | Budget (Rs.) |
| --- | --- | --- | --- |
|  | Improved Poultry breeds | 250 Nos | 25000 |
| Total |  |  | 25000 |

Table: 11. Supply of  bio-products  during 2024-25

| S.No. | Nature of the material supplied | Quantity of bio-product supplied (q) | Budget (Rs.) |
| --- | --- | --- | --- |
| 1 | Vermicompost | 100 | 80000 |
| 2 | Pseudomonas | 1.6 | 28000 |
| Total |  |  | 108000 |

Table:12. Action plan for organizing Extension Activities during 2024-25

| S.No. | Activity | Dates (month) | No. of programmes | No. of participants | Budget required (Rs.) |
| --- | --- | --- | --- | --- | --- |
|  | Field Days (Complete SC OFT/FLD) | November, December and January | 6 | 200 | 10000 |
|  | Kisan Melas | June | 1 | 100 | 21000 |
|  | Technology week | - | - | - | - |
|  | Radio talk | - | - | - | - |
|  | TV talks | - | - | - | - |
|  | Production of CDs (Electronic Media) | - | - | - | - |
|  | Literature | - | 5 | 100 | 25000 |
|  | Evaluation of programmes |  |  |  |  |
|  | Exposure visits |  |  |  |  |
|  | Diagnostic visits |  |  |  |  |
|  | Celebration of important days |  |  |  |  |
|  | Awareness programmes | - | 3 | 90 | 15000 |
|  | Animal health camp | August - December | 5 | 125 | 37500 |
|  |  | Total | 20 | 615 | 108500 |

Table: 13. Action plan for Soil Analysis and issue of Soil health cards during 2024-25

| S.No. | No. of samples | No. of soil health cards to be issued | No. of beneficiaries | Budget (Rs.) |
| --- | --- | --- | --- | --- |
| 1 | 150 | 150 | 150 | 15000 |
|  |  |  | Total | 15000 |

Table: 14.  Action plan for issue of mobile advisories during 2024-25

| S.No | No. of messages | No. of beneficiaries | Budget (Rs.) |
| --- | --- | --- | --- |
|  | 10 | 3000 | - |

Table : 15. Details of micro-enterprises ( physical assets) to be created/ established during 2024-25

| S. No | Name of the micro-enterprise / physical asset to be created | Cost of Critical inputs to be provided (Rs. / unit) |  |  | No. of units to be established | Total Amount to be spent (Rs.)(No. of units x cost /unit) | Total no. of beneficiaries |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Capital (Non-recurring) | General (Recurring) | Total cost (Rs.)/ unit |  |  |  |
| 1 | Sericulture | - | - | - | - | - | - |
| 2 | Apiary | - | - | - | - | - | - |
| 3 | Goatery | - | - | - | - | - | - |
| 4 | Piggery | - | - | - | - | - | - |
| 5 | Poultry | - | - | - | - | - | - |
| 6 | IFS units | - | - | - | - | - | - |
| 7 | Vermicomposting | - | - | - | - | - | - |
| 8 | Mushroom production | - | - | - | - | - | - |
| 9 | Grain storage units | - | - | - | - | - | - |
| 10 | Seed storage units | - | - | - | - | - | - |
| 11 | Primary processing of millets | - | - | - | - | - | - |
| 12 | Value addition | - | - | - | - | - | - |
| 13 | Small farm implements | - | - | - | - | - | - |
| I) | Battery Sprayer | 45000 | 0 | 3000 | 15 | 45000 | 15 |
| ii) | Manual multicrop Seeder | 140000 | 0 | 7000 | 20 | 140000 | 20 |
| iii) | Tree crops Harvester | 26000 | 0 | 6500 | 4 | 26000 | 4 |
| 14 | Threshing floor | - | - | - | - | - | - |
| 15 | Farm ponds / water harvesting structures | - | - | - | - | - | - |
| 16 | Water transportation equipment ( pipes etc.) | - | - | - | - | - | - |
|  | Rain hose | - | 50000 | 25000 | 2 | 50000 | 2 |
| 17 | Water lifting machinery (small motors) | - | - | - | - | - | - |
| 18 | Farm produce cleaning / drying equipment | - | - | - | - | - | - |
| 19 | Any other enterprise (Orchard maintenance) | - | - | - | - | - | - |
|  |  | 211000 | 50000 |  |  | 211000 (SCSP Capital) 50000 (SCSP General) | 39 (SCSP Capital) 2 (SCSP General) |

***  Add rows or add other items based on situation

Table 16. Summary of action plan and budget allocation2024-25

| S.No | Name of the activity | Number of trials /programmes/ units /samples/seed (q)/ Planting or livestock material (No.) | No. of beneficiaries | Budget allocation (Rs.) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Capital | General | Total |
| 1 | OFT | 3 | 6 | - | 39280 | 39280 |
| 2 | FLD | 7 | 28 | - | 52220 | 52220 |
| 3 | Training to PF | 5 | 100 | - | 20000 | 20000 |
| 4 | Training to RY | 2 | 40 | - | 8000 | 8000 |
| 5 | Training to EF | 1 | 20 | - | 4000 | 4000 |
| 6 | Skill training | 3 | 55 | - | 55000 | 55000 |
| 7 | Extension programmes | 20 | 615 | - | 108500 | 108500 |
| 8 | Seed (q) | 8.02 | 50 | - | 115000 | 115000 |
| 9 | Planting material (No.) | 20000 | 10 | - | 30000 | 30000 |
| 10 | Livestock / Fisheries (No.) | 250 | 25 | - | 25000 | 25000 |
| 11 | Bio-products (q) | 101.6 | 25 | - | 108000 | 108000 |
| 12 | Soil samples to be analyzed (No.) | 150 | 150 | - | 15000 | 15000 |
| 12 | Soil health cards (No.) | 150 | 150 | - | - | - |
| 13 | Mobile advisories (No.) | 10 | 3000 | - | - | - |
| 14 | Micro-enterprises / assets to be created (units) |  |  |  |  |  |
| I) | Battery Sprayer | 15 | 15 | 45000 | - | 45000 |
| II) | Manual multicrop Seeder | 20 | 20 | 140000 |  | 140000 |
| III) | Tree crops Harvester | 4 | 4 | 26000 |  | 26000 |
| IV) | Rain hose |  | 2 | - | 50000 | 50000 |
| 15 | Natural farming training programs | 2 | 40 | - | 10000 | 10000 |
|  | Natural farming demonstrations | 2 | 40 | - | 5000 | 5000 |
|  | Natural farming awareness programs | 1 | 50 | - | 5000 | 5000 |
| Total Budget (Rs.) |  |  |  | 211000 | 650000 | 861000 |